## RaportActivitate
Nr. Crt. | Last Name | First Name | Meeting GTKEO | Fisa Cerinte | Meeting Fisa Cerinte | Diagrame | Meeting Diagrame | Implementare Principal | Meeting Implementare Principal | Meeting Interface | Implementare Secundar | Meeting Implementare Secundar | Integrare | Meeting Integrare | Testare Principal | Meeting Testare Principal | Testare Secundar | Meeting Testare Secundar | Meeting Incheiere | Prezentare
1 | Apetroaei | Amalia | X | X | X | X | ―
2 | Cristei | Ioan | X | X | X | X | X |  | X
3 | Danila | Eduard | X | X | X | X | X |  | X
4 | Hreapca | Aurelian | X | X | ― | X | ―
5 | Lionte | Felix | X | X | X | X | X |  | X
6 | Manea | Petru | X | X | X | X | X |  | X
7 | Rotundu | Alin | X | X | ― | X | ― |  | X

## Planificare
Planification Team 3
1) Description of the project and module
Our team has the task to create and implement a disk scanning module, which will be part of a bigger project.
The module will be able to scan a disk and make a list of all the files that it contains, regardless of their status:
visible, hidden, deleted and those that can be restored. Also the module must have the ability to restore files
that have been deleted but not overwriten in the memory.
2) Team members
― Apetroaei Amalia: Team Member
― Cristei Ioan: Team Member
― Danila Eduard: Team Member
― Hreapca Aurelian: Team Member
― Lionte Felix: Team Member
― Manea Petru: Team Leader
― Rotundu Alin: Team Member
3) Milestones
― Getting to know each other : Achieved
― Finding useful information and related project for inspiration and documentation : Achieved
― Creating the Requirements Sheet : Achieved
― Creating the UML Diagrams : Achieved
― Implementation
― Discusion with the interface team
― Reviewing the implementation
― Integration
― Testing
― Discusion with the interface team
― Reviewing the testing
― Final review
― Final meeting
― Presentation
4) Achievements
Week 1
In the first week the asignement was given. There we had our first meeting where we got to know each other.
After we picked the team leader and discussed some of the plans we had for this project, each one of use made
a github account and joined the project. The team leader then had a discussion with the project leader and settled
the tasks that we had to acomplish.
We began documenting and researching. After, we had a meeting where we brain stormed and debated ideas.
We agreed to the best one and started to make the Requirements Sheet. Each one of us made their own version
with the scenarios we each thought are best fitting the module.
Week 2
After a week of research and documenting we each presented our Requirements Sheet. We had a meeting to discuss
each and every one of them. When we finished, all the details were settled on and the team leader made the final version.
Then we started discussing the UML Diagrams and what they'll contain. After a debate we each agreed to take a scenario
and made the Class and Use Case diagram for it.
― Apetroaei Amalia : Opening the Module Diagram
― Cristei Ioan : Interrupting the scan Diagram
― Danila Eduar : Selecting a file Diagram
― Hreapca Aurelian : Refreshing the scan Diagram
― Lionte Felix : Closing the Module Diagram
― Manea Petru : Starting the scan Diagram
― Rotundu Alin : Restoring a file Diagram
― Team : Searching a file Diagram
Week 3
We had a meeting in which we presented and discussed the diagrams for the assignment. After a debate we agreed
on the final details of the diagrams and the team leader made the final version of them.
The hour of truth finally came and we had to present our progress to the client. He was satisfied with the work that
we had done and requested a few changes to some of our ideas. We listened, wrote down and analized his proposal.
We sugested that the decision should be made next week after we had done some research and documentation and
the client agreed upon.
At the end of the week we had another meeting regarding the implementation of the module and we discussed and
debated the modifications that we talked about with the client. After we all agreed on the details we started to implement
the classes and functions for each of our assigned cases.
Week 4
Each one of us created a basic prototype of the classes which he had to implement. We reviewed them and corrected
any mistake that might have slipped through.
5) Future planning
For the next week we plan to continue with the implementation of the module and make the basic functions for scanning. (Week 4)

## Documentatie
Principalele site-uri pentru documentatie
https://www.piriform.com/docs/recuva/technical-information/how-recuva-works
http://www.theabsolute.net/sware/dskinv.html
http://www.hiren.info/articles/recovery/hard-drive-data-recovery-using-disk-investigator